## Slide 1: Local Plan for Census 2020
 | Description | Activity | Timeline
Phase 1 | Field Staff Recruitment | Create awareness of Census 2020 job openings for Address Lister positions | May - Jun 28, 2019
Phase 2 | IET/IELCE Pathway: Digital Literacy Customer Service Communications | Develop curriculum and prepare students for Census 2020 Enumerator positions | July – Sept, 2019
Phase 3 | EL Civics COAAP 54.1 | Educate ESL students on the Census 2020 purpose and process. | Oct - Dec 2019
Phase 4 | Community Awareness Day Campaign “Get Counted” | Work with community partners (United Way, Latino Chamber of Commerce, churches) to encourage community responses to census. | Dec. 2019

## Slide 2: Phase 1: Field Staff Recruitment
Objective: Create awareness of job opportunities and support student application efforts
Strategies:
  Outreach through Social Media
  Connect with students via Email Correspondence
  Website postings
  In-person Recruitment
  Informational Workshops

## Slide 3: Phase 2: IET/IELCE Pathway
Objective: Prepare students for potential Enumerator position with Census 2020
Strategies:
  Provide training:
    digital literacy,
    customer service,
    communications skills
  Offer support for job application process
  Conduct workshops on interviewing skills

## Slide 4: Phase 3: EL Civics COAAPs
Objective: Educate and empower students for the purpose and process of Census 2020
Strategies:
  Develop curriculum
  Provide professional development for instruction
  Provide ELC unit to all ESL classes
  Assess and record results

## Slide 5: Phase 4: “Get Counted” Campaign
Objective: Support community awareness efforts to increase Census responses in the region
Strategies:
  Students share Census 2020 information in the community
    Create student banner and poster sessions
  Practice census survey responses
  Invite community speakers to classes on the importance of being counted